## Progress Planning and Tracking
Project Name: | AC-3 – NibbleAI
Report Date: | 01-26-2025
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3 |  |  |  | Milestone #4 |  |  |  |  | C-Day
Phase | Tasks | Complete% | Current Status Memo | Assigned To | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-04-22 | 1900-01-06
Requirements | Meet with stakeholder(s) SH | 0% |  | Zeynep, Ryan, Austin | 2 | 5 | 5
| Define requirements |  |  | Zeynep, Ryan, Austin
| Review requirements with SH | 0% |  | Zeynep, Ryan, Austin |  | 2 | 5
| Get sign off on requirements | 0% |  | Zeynep, Ryan, Austin |  |  | 5 | 10
Project design | Define tech required * | 0% |  | Austin |  |  |  | 10
| Database design | 0% |  | Austin |  |  |  | 5
| UI design | 0% |  | Zeynep, Austin |  | 5 | 5 | 15 | 2 | 2 | 2 | 2
| ML design | 0% |  | Ryan |  |  | 2 | 7 | 5 | 7
| Develop working prototype | 0% |  | Zeynep, Ryan, Austin | [8 empty] | 6 | 2 | 3 | 3
| Test prototype | 0% |  | Zeynep, Ryan, Austin | [8 empty] | 4 | 8 | 7 | 4
Development | Review prototype design | 0% |  | Zeynep, Ryan, Austin
| Rework requirements | 0% |  | Ryan, Zeynep
| Document updated design | 0% |  | Austin | [15 empty] | 2 | 3
| Test product | 0% |  | Austin | [12 empty] | 15 | 8 | 3 | 3 | 3
Final report | Presentation preparation | 0% |  | Ryan, Austin, Zeynep
| Poster preparation | 0% |  | Ryan, Austin
| Final report submission to D2L and project owner | 0% |  | Zeynep
|  |  | Total work hours | 177 | 2 | 12 | 22 | 47 | 7 | 9 | 2 | 2 | 10 | 10 | 10 | 7 | 15 | 8 | 3 | 5 | 6 | 0 | 0
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours